## Main
| AutoSoft Planner & Buyer Report Version 8.02 |  | 401.996.3631
| J. Serdakowski - 03/14/2022 |  | items on order: | 129
|  |  | insufficient now: | 0
|  |  | insufficient at required date: | 20
|  |  | insufficient after orders: | 0
# | Strategy | Procedure | Last Completed | Duration
1 | Query Maximo to extract a list of all reserved parts in Maximo for all work orders. The results are listed in columns A:AJ of the "Reserved" worksheet. Also extract the current balance for these parts on site and the entire corporation (columns AK:AL). | ExtractReserved | 2024-01-09 14:02 | 0:00
2 | Scans the Reserved worksheet and calculates the remaining inventory after reserve. If the remaining balance equals or exceeds the minimum stocking level, enters "Sufficient Inventory" in Parts Status column (AP). | IdentifyNoProblFromReserve | 2024-01-09 14:02 | 0:00
3 | Extract from Maximo all purchase orders for StoreLoc = "XXX01” that have status of “APPR” and the receipts are not “COMPLETE”. The results are listed in columns A:P of the "Ordered" worksheet. | ExtractOrdered | 2024-01-09 14:02 | 0:00
4 | Compares Orders to Reserved - if existing inventory does not cover reserve, then looks for orders. Identifies if orders will arrive before required. Calculates balances after reserved and orders. | IdentifyOrderStatus | 2024-01-09 14:02 | 0:00
5 | Scans the reserve list. Flags those items which have a negative balance after reserve and do not have anything on order. | FillInRIBalanceAfterOrder | 2024-01-09 14:02 | 0:00
6 | Updates the Parts worksheet | ExtractParts | 2024-01-09 14:04 | 0:02
Include Parts worksheet in update:
Yes
UPDATE
RESERVED WORKSHEET
PARTS WORKSHEET
ORDERS WORKSHEET
PLANNER VIEW
HELP
NEGATIVE BALANCE VIEW
Click on HELP again to hide this.
This file is scheduled to update automatically every night. Look in column D for the last update times of each procedure.
The UPDATE command will manually update the data. Plan on 2 minutes to run the update. The PARTS update takes 3 additional minutes. The default will not update the Parts worksheet. You can also update the Parts worksheet if you change the value of cell B15.
The PLANNER EXCEPTION VIEW will display only those parts that there is insufficient inventory to complete the work order on time.
The NEGATIVE BALANCE VIEW will display only those parts that have insufficient inventory to complete the work order.
The RESERVED WORKSHEET button will bring the user to the entire list of parts and work orders that currently have reservations.
The ORDERS WORKSHEET button will bring the user to a list of all orders currently in Maximo for ARI.
The PARTS WORKSHEET button brings the user to a list of all ARI parts.
LATE DELIVERY ORDERS
OPEN THE MAXIMO PM STATUS REPORT

## Reserved
Parts Reserved in Maximo for site work orders |  |  |  |  | Total Rows: |  |  |  | 47 | items on order: |  | 129 | Report generated at 1/9/2024 2:01:54 PM by jserdako |  |  | It is important to note that the WO Target Start Date is being used to determine if a part arrives on time or late, not the Inventory Reserve Required Date | [9 empty] | This color indicates multiple rows for same part, the number displayed is repeated. This is required to allow sorting. If there is more than one PO, only the first is listed to allow the hyperlink to work. Right click to see all.
[5 empty] | Visible Rows: |  |  |  | 47 | insufficient now: |  | 0
[5 empty] | # of distinct work orders: |  |  |  | 905 | insufficient at required date: |  | 20
[5 empty] | # of distinct z numbers: |  |  |  | 640 | insufficient after orders: |  | 0
[5 empty] | # of WOs changed last 24 hrs: |  |  |  | 167 | [23 empty] | 21.33 | 3.83 | 10.83 | 10.33 | 5.83 | 25.5 | 6.33 | 7.17 | 8.33 | 7.83 | 11 | 14.5 | 11 | 11 | 10.5 | 6.83 | 9.33 | 5.33 | 11.83
w.WONum | p.DisplayName | p.Location | p.Labor | w.Description | w.SafetyCrit | w.Classification | w.WorkType | i.Category | w.Status | r.RequestedDate | w.TargStartDate | w.TargCompDate | r.ItemNum | PartsStatus | t.Description | Manufacturer | i.ModelNum | i.CatalogCode | Vendor | p2.DisplayName | i.MinLevel | i.MaxLevel | r.ReservedQty | RIBalance | RIAfterDemand | PONumber | ArrivalDate | OnOrder | RIAfterOrder | w.NOTESWO | Targ_45 | Arr_Comp_45 | w.Location | w.CCD | w.StatusDate | OrderDate | w.Craft | OrderLate | i.OrderQty | i.IssueYTD | i.Issue1YrAgo | i.DeliveryTime | i.LastIssueDate | r.RequiredDate | w.ReportDate | w.ChangeDate | w.AssetNum | t.LotType | i.Repairable | i.PCS | OtherBalance
WO Num | Planner | WO Location | Labor Group | WO Description | Safety Crit | Classifi- cation | Work Type | Cate-gory | WO Status | InvReserve Request Date | WO Targ Start Date | WO Targ Comp Date | XX Number | Parts Status | Z Number Description | Manufacturer | Model Number | Catalog Code | Vendor | Assigned To | Min Level | Max Level | Reserved Qty | Current RI Balance | RI Balance After Demand | 1st PO Number | Arrival Date | On Order | XX Balance After Orders | WO NOTES | WO Targ Comp. - 45 | Arrival Date - (Comp. - 45) | Location | CCD | WO Status Date | Order Date | Craft | Order Status for Parts with exceptions | Order Qty | Issue YTD | Issue 1 Yr Ago | Delivery Time | Last Issue Date | InvReserve Required Date | WO Report Date | WO Change Date | Asset Number | Lot Type | Repairable | PCS | Current Other Balance
XX6289X3 | XX-MP-02 | XX00566012PSV123527 | XX-MM-09 | XX00566012PSV123527 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 05:25 | 2024-02-01 | 2024-03-01 | XX02376 | ACTIVE | GASKET,SPIRAL WOUND, 3/4" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | XX7X1XXX8 | SXXXX7X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Tony Stark | 110 | 220 | 11 | 226 | 225 |  |  |  | 25 |  | 2024-01-16 | No Arrival Date | XX00566012PSV123527 | 1 | 2023-10-25 05:25 |  | MM | ACTIVE | 1 | 0 | 4 | 27 | 2023-12-09 14:18 | 2024-02-28 | 2023-10-25 05:25 | 2023-10-25 05:25 | 826739 | NOLOT | 0 | 1 | 7
XX6289X6 | XX-MP-02 | XX00566015PSV128615 | XX-MM-09 | XX00566015PSV128615 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 05:25 | 2024-02-01 | 2024-03-01 | XX02376 | ACTIVE | GASKET,SPIRAL WOUND, 3/4" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | XX7X1XXX8 | SXXXX7X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Tony Stark | 110 | 220 | 11 | 226 | 225 |  |  |  | 25 |  | 2024-01-16 | No Arrival Date | XX00566015PSV128615 | 1 | 2023-10-25 05:25 |  | MM | ACTIVE | 1 | 0 | 4 | 27 | 2023-12-09 14:18 | 2024-02-28 | 2023-10-25 05:25 | 2023-10-25 05:25 | 826743 | NOLOT | 0 | 1 | 7
XX62889X | XX-MP-02 | XX00566012PSV123522 | XX-MM-09 | XX00566012PSV123522 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 05:25 | 2024-02-01 | 2024-03-01 | XX02376 | ACTIVE | GASKET,SPIRAL WOUND, 3/4" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | XX7X1XXX8 | SXXXX7X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Tony Stark | 110 | 220 | 11 | 226 | 225 |  |  |  | 25 |  | 2024-01-16 | No Arrival Date | XX00566012PSV123522 | 1 | 2023-10-25 05:25 |  | MM | ACTIVE | 1 | 0 | 4 | 27 | 2023-12-09 14:18 | 2024-02-28 | 2023-10-25 05:25 | 2023-10-25 05:25 | 826736 | NOLOT | 0 | 1 | 7
XX942X55 | XX-MP-02 | XX00566013PSV126522 | XX-MM-09 | XX00566013PSV126522 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-22 04:34 | 2024-03-01 | 2024-04-01 | XX02376 | ACTIVE | GASKET,SPIRAL WOUND, 3/4" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | XX7X1XXX8 | SXXXX7X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Tony Stark | 110 | 220 | 11 | 226 | 225 |  |  |  | 25 |  | 2024-02-16 | No Arrival Date | XX00566013PSV126522 | 1 | 2023-11-22 04:34 |  | MM | ACTIVE | 1 | 0 | 4 | 27 | 2023-12-09 14:18 | 2024-03-28 | 2023-11-22 04:34 | 2023-11-22 04:34 | 826740 | NOLOT | 0 | 1 | 7
XX942X6X | XX-MP-02 | XX00566013PSV126527 | XX-MM-09 | XX00566013PSV126527 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WPARTS | 2023-11-22 04:34 | 2024-03-01 | 2024-04-01 | XX02376 | ACTIVE | GASKET,SPIRAL WOUND, 3/4" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | XX7X1XXX8 | SXXXX7X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Tony Stark | 110 | 220 | 11 | 226 | 225 |  |  |  | 25 |  | 2024-02-16 | No Arrival Date | XX00566013PSV126527 | 1 | 2023-11-22 04:34 |  | MM | ACTIVE | 1 | 0 | 4 | 27 | 2023-12-09 14:18 | 2024-03-28 | 2023-11-22 04:34 | 2023-11-22 04:34 | 826744 | NOLOT | 0 | 1 | 7
XX942X8X | XX-MP-02 | XX00566014PSV124615 | XX-MM-09 | XX00566014PSV124615 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-22 04:34 | 2024-03-01 | 2024-04-01 | XX02376 | ACTIVE | GASKET,SPIRAL WOUND, 3/4" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | XX7X1XXX8 | SXXXX7X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Tony Stark | 110 | 220 | 11 | 226 | 225 |  |  |  | 25 |  | 2024-02-16 | No Arrival Date | XX00566014PSV124615 | 1 | 2023-11-22 04:34 |  | MM | ACTIVE | 1 | 0 | 4 | 27 | 2023-12-09 14:18 | 2024-03-28 | 2023-11-22 04:34 | 2023-11-22 04:34 | 826741 | NOLOT | 0 | 1 | 7
XX62889X | XX-MP-02 | XX00566012PSV123522 | XX-MM-09 | XX00566012PSV123522 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 05:25 | 2024-02-01 | 2024-03-01 | XX02377 | ACTIVE | GASKET,SPIRAL WOUND, 1" PIPE, 150 LB, 304 SS WINDING, FLEXITALLIC | FLEXITALLIC | 162X 1" 15X# | SXX15X3X4-1 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 220 | 40 | 11 | 322 | 311 |  |  |  | 31 |  | 2024-01-16 | No Arrival Date | XX00566012PSV123522 | 1 | 2023-10-25 05:25 |  | MM | ACTIVE | 1 | 0 | 29 | 21 | 2023-12-20 23:27 | 2024-02-28 | 2023-10-25 05:25 | 2023-10-25 05:25 | 826736 | NOLOT | 0 | 0 | 3
XX6289X6 | XX-MP-02 | XX00566015PSV128615 | XX-MM-09 | XX00566015PSV128615 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 05:25 | 2024-02-01 | 2024-03-01 | XX02377 | ACTIVE | GASKET,SPIRAL WOUND, 1" PIPE, 150 LB, 304 SS WINDING, FLEXITALLIC | FLEXITALLIC | 162X 1" 15X# | SXX15X3X4-1 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 220 | 40 | 11 | 322 | 311 |  |  |  | 31 |  | 2024-01-16 | No Arrival Date | XX00566015PSV128615 | 1 | 2023-10-25 05:25 |  | MM | ACTIVE | 1 | 0 | 29 | 21 | 2023-12-20 23:27 | 2024-02-28 | 2023-10-25 05:25 | 2023-10-25 05:25 | 826743 | NOLOT | 0 | 0 | 3
XX6289X3 | XX-MP-02 | XX00566012PSV123527 | XX-MM-09 | XX00566012PSV123527 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 05:25 | 2024-02-01 | 2024-03-01 | XX02377 | ACTIVE | GASKET,SPIRAL WOUND, 1" PIPE, 150 LB, 304 SS WINDING, FLEXITALLIC | FLEXITALLIC | 162X 1" 15X# | SXX15X3X4-1 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 220 | 40 | 11 | 322 | 311 |  |  |  | 31 |  | 2024-01-16 | No Arrival Date | XX00566012PSV123527 | 1 | 2023-10-25 05:25 |  | MM | ACTIVE | 1 | 0 | 29 | 21 | 2023-12-20 23:27 | 2024-02-28 | 2023-10-25 05:25 | 2023-10-25 05:25 | 826739 | NOLOT | 0 | 0 | 3
XX942X6X | XX-MP-02 | XX00566013PSV126527 | XX-MM-09 | XX00566013PSV126527 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WPARTS | 2023-11-22 04:34 | 2024-03-01 | 2024-04-01 | XX02377 | ACTIVE | GASKET,SPIRAL WOUND, 1" PIPE, 150 LB, 304 SS WINDING, FLEXITALLIC | FLEXITALLIC | 162X 1" 15X# | SXX15X3X4-1 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 220 | 40 | 11 | 322 | 311 |  |  |  | 31 |  | 2024-02-16 | No Arrival Date | XX00566013PSV126527 | 1 | 2023-11-22 04:34 |  | MM | ACTIVE | 1 | 0 | 29 | 21 | 2023-12-20 23:27 | 2024-03-28 | 2023-11-22 04:34 | 2023-11-22 04:34 | 826744 | NOLOT | 0 | 0 | 3
XX942X8X | XX-MP-02 | XX00566014PSV124615 | XX-MM-09 | XX00566014PSV124615 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-22 04:34 | 2024-03-01 | 2024-04-01 | XX02377 | ACTIVE | GASKET,SPIRAL WOUND, 1" PIPE, 150 LB, 304 SS WINDING, FLEXITALLIC | FLEXITALLIC | 162X 1" 15X# | SXX15X3X4-1 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 220 | 40 | 11 | 322 | 311 |  |  |  | 31 |  | 2024-02-16 | No Arrival Date | XX00566014PSV124615 | 1 | 2023-11-22 04:34 |  | MM | ACTIVE | 1 | 0 | 29 | 21 | 2023-12-20 23:27 | 2024-03-28 | 2023-11-22 04:34 | 2023-11-22 04:34 | 826741 | NOLOT | 0 | 0 | 3
XX942X55 | XX-MP-02 | XX00566013PSV126522 | XX-MM-09 | XX00566013PSV126522 - PM - VALVE,PRESSURE SAFETY | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-22 04:34 | 2024-03-01 | 2024-04-01 | XX02377 | ACTIVE | GASKET,SPIRAL WOUND, 1" PIPE, 150 LB, 304 SS WINDING, FLEXITALLIC | FLEXITALLIC | 162X 1" 15X# | SXX15X3X4-1 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 220 | 40 | 11 | 322 | 311 |  |  |  | 31 |  | 2024-02-16 | No Arrival Date | XX00566013PSV126522 | 1 | 2023-11-22 04:34 |  | MM | ACTIVE | 1 | 0 | 29 | 21 | 2023-12-20 23:27 | 2024-03-28 | 2023-11-22 04:34 | 2023-11-22 04:34 | 826740 | NOLOT | 0 | 0 | 3
XX9X3X34 | XX-MP-03 | XX00534502AHU510201 | XX-PUO-06 | REPAIR OR REPLACE TV_5102_01, THE BELIMO VALVE FOR HUMIDIFICATION IS NOT OPENING AND CAUSING LOW HUMIDITY ALARMS. THIS WILL REQUIRED ELECTRICAL SUPPORT. VALVE IS SHOWING OPEN ON SIEMEN'S BUT CLOSED IN THE FIELD. | 0 | LEVEL_2 | CM | STK | WSCHD | 2023-11-17 19:06 | 2023-11-16 19:24 | 2023-12-16 19:24 | XX02379 | ACTIVE | GASKET,SPIRAL WOUND, 1-1/2" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | 1.5" 15X# | SXXX15X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 110 | 40 | 22 | 228 | 226 |  |  |  | 27 |  | 2023-11-01 19:24 | No Arrival Date | XX00534502AHU510201 | 0 | 2023-11-17 19:06 |  | PUO | ACTIVE | 1 | 0 | 20 | 17 | 2023-12-15 18:35 | 2023-11-16 19:24 | 2023-11-16 19:24 | 2023-11-17 19:06 | 95001 | NOLOT | 0 | 0 | 8
XX628996 | XX-MP-02 | XX00566012SK123500 | XX-MM-09 | XX00566012SK123500 - PM - SKID | 0 | LEVEL_1 | PM | STK | WSCHD | 2023-10-25 05:26 | 2024-02-01 | 2024-03-01 | XX02379 | ACTIVE | GASKET,SPIRAL WOUND, 1-1/2" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | 1.5" 15X# | SXXX15X1XXX8 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 110 | 40 | 11 | 228 | 227 |  |  |  | 27 |  | 2024-01-16 | No Arrival Date | XX00566012SK123500 | 0 | 2023-10-25 05:26 |  | MM | ACTIVE | 1 | 0 | 20 | 17 | 2023-12-15 18:35 | 2024-02-28 | 2023-10-25 05:26 | 2023-10-25 05:26 | 800779 | NOLOT | 0 | 0 | 8
6268XX45 | XX-MP-03 | XX00518001UNIT001 | XX-PUO-06 | HV-5264-221 LEAKS-BY SLIGHTLY. REBUILD / REPLACE AS NECESSARY. | 0 | LEVEL_3 | CM | STK | WPCOND | 2021-11-10 19:42 | 2021-11-05 16:55 | 2021-12-05 16:55 | XX02382 | ACTIVE | GASKET,SPIRAL WOUND, 3" PIPE, 150 LB, 304 SS WINDING, FLEXITALLIC | FLEXITALLIC | 51X-CC-X15X-3X4-X7 | SXX15X3X4-3 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 110 | 220 | 3 | 119 | 116 |  |  |  | 16 | Outage is needed to perform work. - - kb 7-14-22 SO to determine if OUTAGE required. SSF 5/5/22 WO routed to WPCOND. LOTO for HV-5264-221 will impact all (6) CIP skids, CSG's #1 & 2, & multiple utility stations in XX5. SSF 11/10/21 | 2021-10-21 16:55 | No Arrival Date | XX00518001UNIT001 | 0 | 2021-11-10 19:42 |  | PUO | ACTIVE | 1 | 0 | 3 | 27 | 2023-04-27 13:06 | 2021-11-05 16:55 | 2021-11-05 16:55 | 2022-07-14 19:03 | 509283 | NOLOT | 0 | 0 | 3
XX324944 | XX-MP-03 | XX00518003X526000 | XX-PUO-06 | PLEASE REMOVE CONDENSATE PUMP TO ALLOW FOR CREATION OF MARK-UP TEMPLATE. TEMPLATE WILL BE USED TO ASSIST WITH NEW FLANGE MANUFACTURING TO ALLOW FOR RIGHT THE FIRST TIME ACTIVITIES. TEAM TO INCLUDE RYAN/PAUL/HAWKINS MACHINE/JOHN OLIVER AND TOM F. | 0 | LEVEL_3 | CM | STK | WSCHD | 2023-10-26 16:33 | 2023-10-03 17:46 | 2023-11-02 17:46 | XX02384 | ACTIVE | GASKET,SPIRAL WOUND, 4" PIPE, 150 LB, FLEXITALLIC, PCCS, 304 SS WINDING | FLEXITALLIC | 415X# | SXX15X3X4-4 | FW WEBB COMPANYDBA WEBB BIO PHARM | Steve Rogers | 110 | 220 | 3 | 225 | 2222 |  |  |  | 22 |  | 2023-09-18 17:46 | No Arrival Date | XX00518003X526000 | 0 | 2023-10-26 16:33 |  | PUO | ACTIVE | 1 | 0 | 5 | 14 | 2023-12-05 12:48 | 2023-10-03 17:46 | 2023-10-03 17:46 | 2023-10-26 16:33 | 95046 | NOLOT | 0 | 0 | 24
XX354XX9 | XX-MP-03 | XX01434501AHU02 | XX-PUO-06 | AHU-2 IN CI IS LEAKING WATER FROM GAS COMPARTMENT. INVESTIGATE/REPAIR OR REPLACE AS NECESSARY. DRAIN LINE FROM VENT MAY BE COMPRIMISED. CHANGE ALL AIR FILTERS IN UNIT AS SOME WERE COLLAPSED. | 0 | LEVEL_2 | CM | STK | WSCHD | 2023-10-08 13:11 | 2023-10-08 10:30 | 2023-12-07 10:30 | XX02757 | ACTIVE | FILTER,AIR, 20" SQ X 2" THK, PLEATED ELEMENT, 30% | PUROLATOR PRODUCTS | MX4X-STD2-2X3 | MX4X-STD-2X2X2 | TOTAL FILTRATION SERVICES INCAIRGUARD-CORONA | Steve Rogers | 224 | 48 | 224 | 1146 | 112222 |  |  |  | 122 |  | 2023-10-23 10:30 | No Arrival Date | XX01434501AHU02 | 0 | 2023-10-08 13:11 |  | PUO | ACTIVE | 12 | 0 | 204 | 12 | 2023-12-04 18:45 | 2023-10-08 10:30 | 2023-10-08 10:30 | 2023-10-08 13:11 | 554805 | NOLOT | 0 | 0 | 43
X2XXXX58 | XX-MP-03 | XX01434501AHU01 | XX-PUO-01 | XX01434501AHU01 - PM - AIR HANDLING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:06 | 2024-03-01 | 2024-04-01 | XX02757 | ACTIVE | FILTER,AIR, 20" SQ X 2" THK, PLEATED ELEMENT, 30% | PUROLATOR PRODUCTS | MX4X-STD2-2X3 | MX4X-STD-2X2X2 | TOTAL FILTRATION SERVICES INCAIRGUARD-CORONA | Steve Rogers | 224 | 48 | 224 | 1146 | 112222 |  |  |  | 122 |  | 2024-02-16 | No Arrival Date | XX01434501AHU01 | 0 | 2023-11-29 04:06 |  | PUO | ACTIVE | 12 | 0 | 204 | 12 | 2023-12-04 18:45 | 2024-03-30 | 2023-11-29 04:06 | 2023-11-29 04:06 | 554801 | NOLOT | 0 | 0 | 43
X2XX6X28 | XX-MP-03 | XX00534541EF514104 | XX-PUO-01 | XX00534541EF514104 - PM - FAN,EXHAUST | 0 | LEVEL_3 | PM | STK | WSCHD | 2023-11-29 04:30 | 2024-03-01 | 2024-04-01 | XX02838 | ACTIVE | BELT, V, W .5 INCH, LEN 31 INCH, T .3125 INCH, A29 | GATES | A29 | A29 | BDI INC | Tony Stark | 4 | 6 | 11 | 6 | 5 |  |  |  | 5 |  | 2024-02-16 | No Arrival Date | XX00534541EF514104 | 0 | 2023-11-29 04:30 |  | PUO | ACTIVE | 1 | 0 | 11 | 12 | 2023-07-22 13:04 | 2024-03-30 | 2023-11-29 04:30 | 2023-11-29 04:30 | 97788 | NOLOT | 0 | 0 | 7
X2XX6XX3 | XX-MP-03 | XX00534541EF514103 | XX-PUO-01 | XX00534541EF514103 - PM - FAN,EXHAUST | 0 | LEVEL_3 | PM | STK | WSCHD | 2023-11-29 04:30 | 2024-03-01 | 2024-04-01 | XX03266 | ACTIVE | BELT, V, W .5 INCH, LEN 32 INCH, T .3125 INCH, A30, STATIC DISSIPATING | GATES | A3X | IAX95 | BDI INC | Tony Stark | 11 | 22 | 11 | 3 | 22 |  |  |  | 2 |  | 2024-02-16 | No Arrival Date | XX00534541EF514103 | 0 | 2023-11-29 04:30 |  | PUO | ACTIVE | 1 | 0 | 2 | 12 | 2023-07-26 13:38 | 2024-03-30 | 2023-11-29 04:30 | 2023-11-29 04:30 | 97787 | NOLOT | 0 | 0 | 9
X2X8X86X | XX-MP-03 | XX00634511EF04 | XX-PUO-03 | XX00634511EF04 - PM - FAN,EXHAUST | 0 | LEVEL_3 | PM | STK | WSCHD | 2023-11-29 04:51 | 2024-03-01 | 2024-04-01 | XX05095 | ACTIVE | BELT,V, A32, 34" OUTSIDE CIRCUM, 0.500" TOP WD, 0.3125" THK | GATES | A32 | 6A142 | BDI INC | Tony Stark | 11 | 22 | 22 | 4 | 22 |  |  |  | 2 |  | 2024-02-16 | No Arrival Date | XX00634511EF04 | 0 | 2023-11-29 04:51 |  | PUO | ACTIVE | 1 | 0 | 5 | 17 | 2023-08-24 13:09 | 2024-03-31 | 2023-11-29 04:51 | 2023-11-29 04:51 | 913453 | NOLOT | 0 | 0 | 3
X2XX5X6X | XX-MP-03 | XX01034501EF510101 | XX-PUO-01 | XX01034501EF510101 - PM - FAN,EXHAUST | 0 | LEVEL_3 | PM | STK | WSCHD | 2023-11-29 04:26 | 2024-03-01 | 2024-04-01 | XX05110 | ACTIVE | BELT, W 0.500 TOP WD INCHES, LEN 26 OUTSIDE CIRCUM INCHES, V, 0.3125" THK | GATES | A24 | A24 | BDI INC | Tony Stark | 11 | 11 | 11 | 22 | 11 |  |  |  | 1 |  | 2024-02-16 | No Arrival Date | XX01034501EF510101 | 0 | 2023-11-29 04:26 |  | PUO | ACTIVE | 1 | 0 | 2 | 9 | 2023-07-22 13:03 | 2024-03-30 | 2023-11-29 04:26 | 2023-11-29 04:26 | 100635 | NOLOT | 0 | 0 | 5
XX6X632X | XX-MP-03 | XX00177013BSC015 | XX-PUO-06 | REPAIR BSC AS UNIT CANNOT MEET LOW INFLOW AIR VELOCITY CRITIERIA. REMOVE/REPLACE FILTERS AS NECESSARY AND RE-TAKE CERTIFICATION READINGS | 0 | LEVEL_2 | CMCERT | NS | WPARTS | 2023-10-27 18:10 | 2023-10-24 15:58 | 2023-11-07 15:58 | XX05301 | ACTIVE | FILTER, AIR, W 24 INCH, H 72 INCH, D 6 INCH | NUAIRE | NU-11X-SPEC | A-98XX89-X7 | NUAIRE INC | Steve Rogers | 0 | 0 | 11 |  | -11 |  |  |  | -1 |  | 2023-09-23 15:58 | No Arrival Date | XX00177013BSC015 | 0 | 2023-10-27 18:10 |  | CERT | NEGATIVE BALANCE NO ORDERS | 1 | 0 | 0 | 8 |  | 2023-10-24 15:58 | 2023-10-24 15:58 | 2023-10-27 18:10 | 149354 | NOLOT | 0 | 0
XX6XX664 | XX-MP-03 | XX00534513DC126016 | XX-PUO-01 | XX00534513DC126016 - PM - DUST COLLECTOR | 0 | LEVEL_1 | PM | STK | WSCHD | 2023-10-25 04:08 | 2024-02-01 | 2024-03-01 | XX08101 | ACTIVE | BELT, V, W .5 INCH, LEN 54.3 INCH, T .344 INCH, EXHAUST FAN, A52 | GATES | 9XX2-2X52 | A52 | BDI INC | Tony Stark | 22 | 4 | 11 | 4 | 3 |  |  |  | 3 |  | 2024-01-16 | No Arrival Date | XX00534513DC126016 | 0 | 2023-11-22 13:43 |  | PUO | ACTIVE | 1 | 0 | 2 | 12 | 2023-07-24 18:51 | 2024-02-28 | 2023-10-25 04:08 | 2023-11-22 13:43 | 125321 | NOLOT | 0 | 0 | 6
XX6X93XX | XX-MP-03 | XX00724001X05 | XX-PUO-03 | XX00724001X05 - PM - SKID | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 04:41 | 2024-02-01 | 2024-03-01 | XX08221 | ACTIVE | STRIP, MINNCARE, PLASTIC, 1 PERCENT TEST, MAR COR MINNCARE 1% TEST, VIAL OF 100 STRIPS (CANADIAN PART NO. 78339-000) | MINNTECHFILTRATION TECH GROUP | 185-4X-XX5 | 78339-XXX | NORTHEAST WATER SVCS INC | Bruce Banner | 22 | 4 | 11 | 4 | 3 |  |  |  | 3 |  | 2024-01-16 | No Arrival Date | XX00724001X05 | 0 | 2023-10-25 04:41 |  | PUO | ACTIVE | 1 | 0 | 5 | 14 | 2023-10-19 17:52 | 2024-02-28 | 2023-10-25 04:41 | 2023-10-25 04:41 | 95812 | LOT | 0 | 0 | 8
X24X46XX | XX-MP-03 | XX00534541EF514101 | XX-PUO-01 | XX00534541EF514101 - PM - FAN,EXHAUST | 0 | LEVEL_3 | PM | STK | WSCHD | 2023-12-27 04:42 | 2024-04-01 | 2024-05-01 | XX08223 | ACTIVE | BELT,V, B38, 41" OUTSIDE CIRCUM, 0.65625" TOP WD, 0.4375" THK | GATES | B38 | B38 | BDI INC | Tony Stark | 22 | 4 | 11 | 6 | 5 |  |  |  | 5 |  | 2024-03-17 | No Arrival Date | XX00534541EF514101 | 0 | 2023-12-27 04:42 |  | PUO | ACTIVE | 1 | 0 | 4 | 16 | 2023-09-18 10:56 | 2024-04-30 | 2023-12-27 04:42 | 2023-12-27 04:42 | 101037 | NOLOT | 0 | 0 | 6
X24X499X | XX-MP-03 | XX00534541EF514102 | XX-PUO-01 | XX00534541EF514102 - PM - FAN,EXHAUST | 0 | LEVEL_3 | PM | STK | WSCHD | 2023-12-27 04:44 | 2024-04-01 | 2024-05-01 | XX08223 | ACTIVE | BELT,V, B38, 41" OUTSIDE CIRCUM, 0.65625" TOP WD, 0.4375" THK | GATES | B38 | B38 | BDI INC | Tony Stark | 22 | 4 | 11 | 6 | 5 |  |  |  | 5 |  | 2024-03-17 | No Arrival Date | XX00534541EF514102 | 0 | 2023-12-27 04:44 |  | PUO | ACTIVE | 1 | 0 | 4 | 16 | 2023-09-18 10:56 | 2024-04-30 | 2023-12-27 04:44 | 2023-12-27 04:44 | 101035 | NOLOT | 0 | 0 | 6
XX6X94X5 | XX-MP-03 | XX00724001X01 | XX-PUO-03 | XX00724001X01 - PM - SKID | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 04:42 | 2024-02-01 | 2024-03-01 | XX100544 | ACTIVE | FILTER, 5 MICRON, PRETREATMENT, 20" | US FILTER | FCROF2XX5 | W2T856216 | EVOQUA WATER TECHNOLOGIES | Steve Rogers | 110 | 220 | 22 | 220 | 118 |  |  |  | 18 |  | 2024-01-16 | No Arrival Date | XX00724001X01 | 0 | 2023-10-25 04:42 |  | PUO | ACTIVE | 1 | 0 | 10 | 12 | 2023-10-25 14:27 | 2024-02-28 | 2023-10-25 04:42 | 2023-10-25 04:42 | 95751 | NOLOT | 0 | 0
XX6X94X5 | XX-MP-03 | XX00724001X01 | XX-PUO-03 | XX00724001X01 - PM - SKID | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 04:42 | 2024-02-01 | 2024-03-01 | XX100568 | ACTIVE | FILTER, 10 MICRON, PRETREATMENT, 20" | US FILTER | FCROF2X1X | FCROF2X1X | TOTAL FILTRATION SERVICES INC | Steve Rogers | 6 | 1122 | 22 | 114 | 116 |  |  |  | 16 |  | 2024-01-16 | No Arrival Date | XX00724001X01 | 0 | 2023-10-25 04:42 |  | PUO | ACTIVE | 1 | 0 | 8 | 20 | 2023-10-09 06:32 | 2024-02-28 | 2023-10-25 04:42 | 2023-10-25 04:42 | 95751 | NOLOT | 0 | 0
6268XX45 | XX-MP-03 | XX00518001UNIT001 | XX-PUO-06 | HV-5264-221 LEAKS-BY SLIGHTLY. REBUILD / REPLACE AS NECESSARY. | 0 | LEVEL_3 | CM | STK | WPCOND | 2021-11-10 19:42 | 2021-11-05 16:55 | 2021-12-05 16:55 | XX101841 | ACTIVE | VALVE,GATE, 3", 150 LB, FLANGED, CARBON STEEL BODY | CRANE CO | 47XUF-3 | 547X | FW WEBB COMPANYDBA WEBB BIO PHARM | Bruce Banner | 11 | 11 | 11 | 22 | 11 |  |  |  | 1 | Outage is needed to perform work. - - kb 7-14-22 SO to determine if OUTAGE required. SSF 5/5/22 WO routed to WPCOND. LOTO for HV-5264-221 will impact all (6) CIP skids, CSG's #1 & 2, & multiple utility stations in XX5. SSF 11/10/21 | 2021-10-21 16:55 | No Arrival Date | XX00518001UNIT001 | 0 | 2021-11-10 19:42 |  | PUO | ACTIVE | 1 | 0 | 0 | 30 | 2014-07-16 19:33 | 2021-11-05 16:55 | 2021-11-05 16:55 | 2022-07-14 19:03 | 509283 | NOLOT | 0 | 0 | 0
XX9XX852 | XX-MP-02 | XX00566508SK160100 | XX-MM-09 | PERFORM JP: 141604 ON ASSET 127148. | 0 | LEVEL_1 | GM | STK | WSCHD | 2023-12-26 14:24 | 2023-11-14 18:31 | 2024-01-13 18:31 | XX102352 | ACTIVE | KIT, REBUILD, FOR SVF-A05AA1A/B SIGHT GLASS | LJ STAR INC | KSVF-X5-AA | KSVF-X5-AA | AVANTOR FLUID HANDLING LLC | Steve Rogers | 115 | 225 | 11 | 225 | 224 |  |  |  | 24 | ACCIDENTALLY MOVED PXXENT WO 69541844 TO INPRG WHICH MADE THIS CHILD MOVE TO INPRG. MOVED BACK TO WSCHD per Cheryl H. - kb 12-26-23 | 2023-11-29 18:31 | No Arrival Date | XX00566508SK160100 | 0 | 2023-12-26 14:24 |  | MM | ACTIVE | 1 | 0 | 38 | 31 | 2023-12-15 16:55 | 2023-11-14 18:31 | 2023-11-14 18:31 | 2023-12-26 14:24 | 127148 | NOLOT | 0 | 1 | 4
X2XX3368 | XX-MP-03 | XX00634503CRAC08 | XX-PUO-01 | XX00634503CRAC08 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:13 | 2024-03-01 | 2024-04-01 | XX102534 | ACTIVE | BELT,V, B41, 44" OUTSIDE CIRCUM, 0.65625" TOP WD, 0.4375" THK | GATES | B41 | B41 | BDI INC | Tony Stark | 11 | 22 | 22 | 6 | 4 |  |  |  | 4 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC08 | 0 | 2023-11-29 04:13 |  | PUO | ACTIVE | 1 | 0 | 8 | 12 | 2023-09-18 13:05 | 2024-03-30 | 2023-11-29 04:13 | 2023-11-29 04:13 | 533241 | NOLOT | 0 | 0
X2XX32X3 | XX-MP-03 | XX00634503CRAC09 | XX-PUO-01 | XX00634503CRAC09 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:13 | 2024-03-01 | 2024-04-01 | XX102534 | ACTIVE | BELT,V, B41, 44" OUTSIDE CIRCUM, 0.65625" TOP WD, 0.4375" THK | GATES | B41 | B41 | BDI INC | Tony Stark | 11 | 22 | 22 | 6 | 4 |  |  |  | 4 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC09 | 0 | 2023-11-29 04:13 |  | PUO | ACTIVE | 1 | 0 | 8 | 12 | 2023-09-18 13:05 | 2024-03-30 | 2023-11-29 04:13 | 2023-11-29 04:13 | 533240 | NOLOT | 0 | 0
XX6X93XX | XX-MP-03 | XX00724001X05 | XX-PUO-03 | XX00724001X05 - PM - SKID | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-10-25 04:41 | 2024-02-01 | 2024-03-01 | XX102798 | ACTIVE | STRIP, MINNCARE, RESIDUAL TEST | MINNTECHFILTRATION TECH GROUP | 78338-XX | 78338-XX | NORTHEAST WATER SVCS INC | Steve Rogers | 11 | 22 | 11 | 4 | 3 |  |  |  | 3 |  | 2024-01-16 | No Arrival Date | XX00724001X05 | 0 | 2023-10-25 04:41 |  | PUO | ACTIVE | 1 | 0 | 5 | 15 | 2023-10-19 17:52 | 2024-02-28 | 2023-10-25 04:41 | 2023-10-25 04:41 | 95812 | LOT | 0 | 0 | 0
X2XX32X3 | XX-MP-03 | XX00634503CRAC09 | XX-PUO-01 | XX00634503CRAC09 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:13 | 2024-03-01 | 2024-04-01 | XX103001 | ACTIVE | FILTER, AIR, 20" X 25" X 2", 60% EFFICIENT (MERV II) | FLANDERS FILTERS INC. | 85655.X2.2X25 M11 | 85655.X2.2X25M11 | FLANDERS CORPDBA FLANDERS FILTERS INC | Steve Rogers | 110 | 322 | 22 | 30 | 228 |  |  |  | 28 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC09 | 0 | 2023-11-29 04:13 |  | PUO | ACTIVE | 1 | 0 | 16 | 30 | 2023-11-17 11:46 | 2024-03-30 | 2023-11-29 04:13 | 2023-11-29 04:13 | 533240 | NOLOT | 0 | 0
X2XX3368 | XX-MP-03 | XX00634503CRAC08 | XX-PUO-01 | XX00634503CRAC08 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:13 | 2024-03-01 | 2024-04-01 | XX103001 | ACTIVE | FILTER, AIR, 20" X 25" X 2", 60% EFFICIENT (MERV II) | FLANDERS FILTERS INC. | 85655.X2.2X25 M11 | 85655.X2.2X25M11 | FLANDERS CORPDBA FLANDERS FILTERS INC | Steve Rogers | 110 | 322 | 22 | 30 | 228 |  |  |  | 28 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC08 | 0 | 2023-11-29 04:13 |  | PUO | ACTIVE | 1 | 0 | 16 | 30 | 2023-11-17 11:46 | 2024-03-30 | 2023-11-29 04:13 | 2023-11-29 04:13 | 533241 | NOLOT | 0 | 0
XX96XX48 | XX-MP-03 | XX00634503CRAC04 | XX-PUO-06 | UNIT IS TRIPPING OFF ON A PRE-HEAT FAILURE ALARM. TROUBLE SHOOT AND REPAIR AS NECESSARY. THE BELTS ALSO NEED TO BE ADJUSTED. | 0 | LEVEL_2 | CM | NS | WPARTS | 2024-01-03 19:12 | 2023-11-23 09:25 | 2024-01-22 09:25 | XX103016 | ACTIVE | PULLEY, 2 GROOVE, VAR, BORED 4.3" - 5.5" PITCH DIA | STULZ GMBH HUMIDIFICATION | PULV25522 |  | STULZ AIR TECHNOLOGY SYSTEMS INC | Tony Stark | 0 | 0 | 11 | 11 | 0 |  |  |  | 0 | Unit needs 4 beXXings (Z133942) 1 Shaft (Z180820) 1 pulley (Z103016) 1 Pulley (Z103017) 2 Belts (z41121) DD 1/3/24 | 2023-12-08 09:25 | No Arrival Date | XX00634503CRAC04 | 0 | 2024-01-03 19:12 |  | PUO | ACTIVE | 1 | 0 | 0 | 30 | 2022-07-13 18:16 | 2023-11-23 09:25 | 2023-11-23 09:25 | 2024-01-03 19:12 | 533235 | NOLOT | 0 | 0
XX96XX48 | XX-MP-03 | XX00634503CRAC04 | XX-PUO-06 | UNIT IS TRIPPING OFF ON A PRE-HEAT FAILURE ALARM. TROUBLE SHOOT AND REPAIR AS NECESSARY. THE BELTS ALSO NEED TO BE ADJUSTED. | 0 | LEVEL_2 | CM | NS | WPARTS | 2024-01-03 19:12 | 2023-11-23 09:25 | 2024-01-22 09:25 | XX103017 | ACTIVE | PULLEY, 2 GROOVE, FIXED, BUSHED 7.4" PITCH | STULZ GMBH HUMIDIFICATION | PULF74X9X |  | STULZ AIR TECHNOLOGY SYSTEMS INC | Tony Stark | 0 | 0 | 11 | 22 | -11 |  |  |  | -1 | Unit needs 4 beXXings (Z133942) 1 Shaft (Z180820) 1 pulley (Z103016) 1 Pulley (Z103017) 2 Belts (z41121) DD 1/3/24 | 2023-12-08 09:25 | No Arrival Date | XX00634503CRAC04 | 0 | 2024-01-03 19:12 |  | PUO | NEGATIVE BALANCE NO ORDERS | 1 | 0 | 0 | 30 | 2021-04-13 16:02 | 2023-11-23 09:25 | 2023-11-23 09:25 | 2024-01-03 19:12 | 533235 | NOLOT | 0 | 0
X2XX3X2X | XX-MP-03 | XX00634503CRAC04 | XX-PUO-01 | XX00634503CRAC04 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:12 | 2024-03-01 | 2024-04-01 | XX103087 | ACTIVE | FILTER,AIR, 18" X 24" X 4", PLEATED ELEMENT, 40% | PUROLATOR PRODUCTS | DP4X-STD4-412 | MX4X-STD4-412 | NORTHEAST AIR SOLUTIONS INC | Steve Rogers | 6 | 118 | 4 | 36 | 322 |  |  |  | 32 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC04 | 0 | 2023-11-29 04:12 |  | PUO | ACTIVE | 6 | 0 | 82 | 24 | 2023-12-20 15:05 | 2024-03-30 | 2023-11-29 04:12 | 2023-11-29 04:12 | 533235 | NOLOT | 0 | 0
X2XX29X5 | XX-MP-03 | XX00634503CRAC02 | XX-PUO-01 | XX00634503CRAC02 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:12 | 2024-03-01 | 2024-04-01 | XX103087 | ACTIVE | FILTER,AIR, 18" X 24" X 4", PLEATED ELEMENT, 40% | PUROLATOR PRODUCTS | DP4X-STD4-412 | MX4X-STD4-412 | NORTHEAST AIR SOLUTIONS INC | Steve Rogers | 6 | 118 | 4 | 36 | 322 |  |  |  | 32 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC02 | 0 | 2023-11-29 04:12 |  | PUO | ACTIVE | 6 | 0 | 82 | 24 | 2023-12-20 15:05 | 2024-03-30 | 2023-11-29 04:12 | 2023-11-29 04:12 | 533239 | NOLOT | 0 | 0
X2XX29XX | XX-MP-03 | XX00634503CRAC01 | XX-PUO-01 | XX00634503CRAC01 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:11 | 2024-03-01 | 2024-04-01 | XX103087 | ACTIVE | FILTER,AIR, 18" X 24" X 4", PLEATED ELEMENT, 40% | PUROLATOR PRODUCTS | DP4X-STD4-412 | MX4X-STD4-412 | NORTHEAST AIR SOLUTIONS INC | Steve Rogers | 6 | 118 | 4 | 36 | 322 |  |  |  | 32 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC01 | 0 | 2023-11-29 04:11 |  | PUO | ACTIVE | 6 | 0 | 82 | 24 | 2023-12-20 15:05 | 2024-03-30 | 2023-11-29 04:11 | 2023-11-29 04:11 | 533238 | NOLOT | 0 | 0
X2XX3XXX | XX-MP-03 | XX00634503CRAC03 | XX-PUO-01 | XX00634503CRAC03 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:12 | 2024-03-01 | 2024-04-01 | XX103087 | ACTIVE | FILTER,AIR, 18" X 24" X 4", PLEATED ELEMENT, 40% | PUROLATOR PRODUCTS | DP4X-STD4-412 | MX4X-STD4-412 | NORTHEAST AIR SOLUTIONS INC | Steve Rogers | 6 | 118 | 4 | 36 | 322 |  |  |  | 32 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC03 | 0 | 2023-11-29 04:12 |  | PUO | ACTIVE | 6 | 0 | 82 | 24 | 2023-12-20 15:05 | 2024-03-30 | 2023-11-29 04:12 | 2023-11-29 04:12 | 533234 | NOLOT | 0 | 0
X2XX293X | XX-MP-03 | XX00634503CRAC06 | XX-PUO-01 | XX00634503CRAC06 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:11 | 2024-03-01 | 2024-04-01 | XX103088 | ACTIVE | FILTER,AIR, 14" X 25" X 2", PLEATED ELEMENT, 40% | PUROLATOR PRODUCTS | DP4X-STD2-241 | DP4X-STD2-241 | TOTAL FILTRATION SERVICES INCAIRGUARD-CORONA | Steve Rogers | 3 | 6 | 3 | 223 | 220 |  |  |  | 20 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC06 | 0 | 2023-11-29 04:11 |  | PUO | ACTIVE | 6 | 0 | 24 | 14 | 2023-11-21 18:31 | 2024-03-30 | 2023-11-29 04:11 | 2023-11-29 04:11 | 533237 | NOLOT | 0 | 0
X2XX3X53 | XX-MP-03 | XX00634503CRAC05 | XX-PUO-01 | XX00634503CRAC05 - PM - AIR CONDITIONING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:12 | 2024-03-01 | 2024-04-01 | XX103088 | ACTIVE | FILTER,AIR, 14" X 25" X 2", PLEATED ELEMENT, 40% | PUROLATOR PRODUCTS | DP4X-STD2-241 | DP4X-STD2-241 | TOTAL FILTRATION SERVICES INCAIRGUARD-CORONA | Steve Rogers | 3 | 6 | 3 | 223 | 220 |  |  |  | 20 |  | 2024-02-16 | No Arrival Date | XX00634503CRAC05 | 0 | 2023-12-18 21:34 |  | PUO | ACTIVE | 6 | 0 | 24 | 14 | 2023-11-21 18:31 | 2024-03-30 | 2023-11-29 04:12 | 2023-12-18 21:34 | 533236 | NOLOT | 0 | 0
X2XX32X3 | XX-MP-03 | XX00634501AHU04 | XX-PUO-01 | XX00634501AHU04 - PM - AIR HANDLING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-11-29 04:13 | 2024-03-01 | 2024-04-01 | XX10419 | ACTIVE | FILTER,AIR, 24" SQ X 2" THK, PLEATED ELEMENT, MERV 8A EFFICIENT, UL-900 RATED | CAMFIL FARR CO. | X4988XXX5 | FC3X22424 | FILTER SALES AND SVC INC | Steve Rogers | 2240 | 480 | 224 | 375 | 3511 |  |  |  | 351 |  | 2024-02-16 | No Arrival Date | XX00634501AHU04 | 0 | 2023-11-29 04:13 |  | PUO | ACTIVE | 12 | 46 | 1223 | 21 | 2024-01-05 14:27 | 2024-03-30 | 2023-11-29 04:13 | 2023-11-29 04:13 | 533218 | NOLOT | 0 | 0
X24X896X | XX-MP-03 | XX00634501AHU03 | XX-PUO-01 | XX00634501AHU03 - PM - AIR HANDLING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-12-27 04:15 | 2024-04-01 | 2024-05-01 | XX10419 | ACTIVE | FILTER,AIR, 24" SQ X 2" THK, PLEATED ELEMENT, MERV 8A EFFICIENT, UL-900 RATED | CAMFIL FARR CO. | X4988XXX5 | FC3X22424 | FILTER SALES AND SVC INC | Steve Rogers | 2240 | 480 | 224 | 375 | 3511 |  |  |  | 351 |  | 2024-03-17 | No Arrival Date | XX00634501AHU03 | 0 | 2023-12-27 04:15 |  | PUO | ACTIVE | 12 | 46 | 1223 | 21 | 2024-01-05 14:27 | 2024-04-30 | 2023-12-27 04:15 | 2023-12-27 04:15 | 533219 | NOLOT | 0 | 0
X24X948X | XX-MP-03 | XX00634501AHU01 | XX-PUO-01 | XX00634501AHU01 - PM - AIR HANDLING UNIT | 0 | LEVEL_2 | PM | STK | WSCHD | 2023-12-27 04:18 | 2024-04-01 | 2024-05-01 | XX10419 | ACTIVE | FILTER,AIR, 24" SQ X 2" THK, PLEATED ELEMENT, MERV 8A EFFICIENT, UL-900 RATED | CAMFIL FARR CO. | X4988XXX5 | FC3X22424 | FILTER SALES AND SVC INC | Steve Rogers | 2240 | 480 | 224 | 375 | 3511 |  |  |  | 351 |  | 2024-03-17 | No Arrival Date | XX00634501AHU01 | 0 | 2023-12-27 04:18 |  | PUO | ACTIVE | 12 | 46 | 1223 | 21 | 2024-01-05 14:27 | 2024-04-30 | 2023-12-27 04:18 | 2023-12-27 04:18 | 533224 | NOLOT | 0 | 0
Formulas:
Targ_45 = [w.TargCompDate] - 45
PLANNER VIEW
SHOW ALL ROWS
SORT ASC.
SORT DESC.
HELP
SHOW ALL COLUMNS
NEGATIVE BALANCE VIEW
ORDERS
PARTS
MAIN
Click on HELP again to hide this.
RIGHT CLICK on a cell will bring you to a list of orders for that part, or jump to the parts screen for more details on the part.
Have Maximo open and double click on a hyperlink will bring you to that record.
PLANNER EXCEPTION VIEW will display only those parts with issues
NEGATIVE BALANCE VIEW will display only those parts with negative balances after orders
SHOW ALL ROWS will display all records
SHOW ALL COLUMNS/HIDE SOME COLUMNS will toggle additional columns
SORT ASC./SORT DESC. will sort the list based on the selected columns. Note: This worksheet is protected, the password is "aaa", AutoFiltering works, howver you cannot sort a protected document using the sort feature in the AutoFilter.
MAIN, ORDERS, PARTS brings you to those worksheets.
RIGHT CLICK ON A CELL TO JUMP TO MORE INFORMATION ABOUT THAT PART ON THE ORDERS & PARTS SHEETS

## Orders
All Parts On Order in Maximo at this site |  |  |  | Report generated at 1/9/2024 2:02:02 PM by jserdako on USLV-PAPP-MAT01
Total Rows: | 34 |  |  | Rows where Vendor Delivery Date is later than Required: | 8 | 23.53%
Visible Rows: | 34
pl.ItemNum | pl.Description | po.PONum | pl.POLineNum | po.Description | po.PurchaseAgent | po.OrderDate | pl.ReqDeliveryDate | po.Status | po.Vendor | pl.VenDeliveryDate | pl.ModelNum | pl.CatalogCode | pl.OrderQty | pl.RequestedBy | pl.Manufacturer | Order_Comments | Order_Status
Item Num | Item Number Description | PO Num | PO Line | PO Description | Purchase Agent | Order Date | Required Date | PO Status | Vendor | Ven Delivery Date | Model Num | Catalog Code | Order Qty | Requested By | Manufacturer | Order Comments | Order Status
Z01210 | ELBOW, 1-1/2", TRI-CLAMP, 316L SS, 240/EP, 90 DEG | E3865-3155 | 1 | FW WEBB CO ¦ REF QUOTE#: 81005470 | BRYAN COLBURN | 2023-06-06 15:43 | 2023-06-16 | APPR | FERGUSON INDUSTRIAL GROUP | 2023-06-16 | B2CMP-1.5-316L-PM |  | 1 | MXINTADM |  |  | No WOs requiring this part
Z01229 | CAP, PORT, 3", 316L SS, 240/EP | M100141352 | 9 | INTERNAL TRANSFER - AWM TO ARI | CHRISTOPHER STENNING | 2021-10-21 16:34 | 2021-10-21 | APPR |  |  | 16AMP3-316L-PM |  | 3 | CHRISTOPHER STENNING | ALFALAV1 |  | No WOs requiring this part
Z01230 | CAP, PORT, 4", 316L SS, 240/EP | M100141352 | 16 | INTERNAL TRANSFER - AWM TO ARI | CHRISTOPHER STENNING | 2021-10-21 16:34 | 2021-10-21 | APPR |  |  | 16AMP-4-316L-PM |  | 4 | CHRISTOPHER STENNING | TRICLOV1 |  | No WOs requiring this part
Z01233 | CAP, END, SZ 0.5 & 0.75 INCH, 316L SS, 240EP | M100141352 | 1 | INTERNAL TRANSFER - AWM TO ARI | CHRISTOPHER STENNING | 2021-10-21 16:34 | 2021-10-21 | APPR |  |  | 16AMP-.75-316L-PM |  | 10 | CHRISTOPHER STENNING | ALFALAV1 |  | No WOs requiring this part
Z05085 | KIT, REBUILD, SS 316, FOR 1/2" , 3/4" BT6-BT6F-BTM7 TRAP, CONTAINS ELEMENT , CLIP ASSEMBLY | M100141352 | 17 | INTERNAL TRANSFER - AWM TO ARI | CHRISTOPHER STENNING | 2021-10-21 16:34 | 2021-10-21 | APPR |  |  | 1800080 |  | 2 | CHRISTOPHER STENNING | SPIRAXS1 |  | No WOs requiring this part
Z100021 | PROBE, GLASS, STNDS PH ELECTRODE MODEL F-235 | F3865-1270 | 1 | BROADLEY JAMES CORP ¦ REF QUOTE#: QUO5426 | BRYAN COLBURN | 2023-11-09 14:17 | 2023-12-22 | APPR | FERGUSON INDUSTRIAL GROUP | 2023-12-22 | F-235-D120-VP | F-235-D120-VP | 93 | MXINTADM | BROADLE1 |  | No WOs requiring this part
Z100170 | KIT, MECHANICAL SEAL, SX4 SERIES PUMP, KIT CONTAINS ONE OF E | E3865-3161 | 1 | WOLSELEY INDUSTRIAL F2850 ¦ REF QUOTE#: B510969 | BRYAN COLBURN | 2023-06-06 09:25 | 2023-06-16 | APPR | FERGUSON INDUSTRIAL GROUP | 2023-06-16 | 9630088497 |  | 1 | MXINTADM | ALFALAV1 |  | No WOs requiring this part
Z100174 | RING, JOINT, EPDM, COVER PLATE, EPDM USP CLASS VI, COMPRESSION JOINT RING | E3865-3161 | 2 | WOLSELEY INDUSTRIAL F2850 ¦ REF QUOTE#: B510969 | BRYAN COLBURN | 2023-06-06 09:25 | 2023-06-21 | APPR | FERGUSON INDUSTRIAL GROUP | 2023-06-21 | 9630070401 |  | 1 | MXINTADM | ALFALAV1 |  | No WOs requiring this part
Z101170 | FILTER, AIR, HVAC, 24 INCH SQ X 12 INCH THK, DURAFIL, 95% EFFIC. | F3865-1766 | 2 | FILTER SALES & SERVICE INC ¦ REF QUOTE#: 11176097 | BRYAN COLBURN | 2024-01-03 13:57 | 2024-01-26 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-26 | 855080009 | 855080009 | 30 | MXINTADM | CAMFILF1 |  | No WOs requiring this part
Z102618 | SENSOR, PH/ORP, PT 100, TITANIUM TUBE, LOW RESISTANCE GLASS, | E3865-2978 | 2 | POND TECHNICAL SALES INC ¦ ----- REF QUOTE # QA35525 | ALEXANDREA TONDREAU | 2023-12-18 08:54 | 2023-06-30 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-02-09 | 23566-00 |  | 2 | MXINTADM | ROSEMOU1 |  | No WOs requiring this part
Z104599 | BAG, REF# 516 (RETAINS 99.7% @ 3 MICRONS VACUUM DISPOSABLE P | E3865-1386 | 1 | NILFISK ADVANCE INC ¦ | ALEXANDREA TONDREAU | 2023-01-04 13:14 | 2023-01-11 | APPR | FERGUSON INDUSTRIAL GROUP | 2023-01-11 | 81620000 |  | 1 | MXINTADM | NILFISK1 | Committed to WO #71628279
Z104607 | FILTER 0.12 MICRON REPLACEMENT (RETAINS 99.999%) ULPA CAR | F3865-1779 | 1 | NILFISK ADVANCE INC ¦ REF QUOTE#: 101028204 | BRYAN COLBURN | 2024-01-04 11:40 | 2024-01-12 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-12 | 01737631 | 01737631 | 13 | MXINTADM | NILFISK1 | Committed to WO #71628279
Z104959 | O-RING, SHAFT SEAL, ID 1.8125 INH, OD 2 INH, W 0.09375 INH, | E3865-3308 | 1 | PERRIGO INC ¦ | CHRISTOPHER STENNING | 2023-06-16 09:00 | 2023-07-28 | APPR | FERGUSON INDUSTRIAL GROUP | 2023-07-28 | USPE70133 |  | 10 | MXINTADM | WAUKESH1 |  | No WOs requiring this part
Z106012 | SOLUTION, TURBIDITY, 450PPM; 1.0? M MM STABILIZED POLYMER SUSPENSION 450 PPM NOM. 500 ML | F3865-1348 | 1 | OPTEK DANULAT INC ¦ REF QUOTE: USAQ45428 | BRYAN COLBURN | 2023-12-20 14:28 | 2023-12-03 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-26 | 9210-0450-05 | 9210-0450-05 | 1 | MXINTADM | OPTEKDA1 |  | No WOs requiring this part
Z106058 | MODULE, SPEED CONTROL, DOOR CLOSING | F3865-1776 | 1 | DORMAKABA USA INC BOSTON ¦ REF QUOTE#: 1750038007 | BRYAN COLBURN | 2024-01-04 10:36 | 2024-01-12 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-12 | 3428 |  | 2 | MXINTADM |  |  | No WOs requiring this part
Z108069 | PLATE,WALL, DUPLEX RECEPTACLE, 1 GANG, WEATHERPROOF, COVER | F3865-1777 | 4 | GRANITE CITY ELECTRIC SUPPLY ¦ REF QUOTE#: S009582213 | BRYAN COLBURN | 2024-01-04 11:32 | 2024-01-19 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-19 | CA8GV | CA8GV | 14 | MXINTADM | PASS&SE1 |  | No WOs requiring this part
Z108653 | STEAM VALVE BRASS(2 ) | F3865-1448 | 1 | SIEMENS HEALTHCARE DIAGNOSTICS ¦ REF QUOTE#: B17 - 2002182925 | BRYAN COLBURN | 2023-12-21 10:54 | 2023-12-15 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-12 | 599-03062 |  | 1 | MXINTADM | SIEMENS3 | Committed to WO #71945974
Z110086 | SCREEN, LAYERED MESH, 316L SS, 160 CM, BOTTOM, O/D 1611.60MM | F3865-944 | 6 | ROCKY MOUNTAIN PROCESS ¦ | CHRISTOPHER STENNING | 2023-10-18 15:26 | 2024-03-17 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-02-02 | 110706 |  | 7 | MXINTADM | GBOPP1 | Committed to WO #72302659
Z110086 | SCREEN, LAYERED MESH, 316L SS, 160 CM, BOTTOM, O/D 1611.60MM | F3865-947 | 6 | ROCKY MOUNTAIN PROCESS ¦ | CHRISTOPHER STENNING | 2023-10-18 15:46 | 2024-03-17 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-05-17 | 110706 |  | 4 | MXINTADM | GBOPP1 | Order arrives 60 days late for WO #72302659
Z110086 | SCREEN, LAYERED MESH, 316L SS, 160 CM, BOTTOM, O/D 1611.60MM | F3865-948 | 6 | ROCKY MOUNTAIN PROCESS ¦ | CHRISTOPHER STENNING | 2023-10-18 15:58 | 2024-03-17 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-08-30 | 110706 |  | 3 | MXINTADM | GBOPP1 | Order arrives 165 days late for WO #72302659
Z110094 | SCREEN, LAYERED MESH, 316L SS, 160 CM, TOP, O/D 1592.4 MM X | F3865-944 | 5 | ROCKY MOUNTAIN PROCESS ¦ | CHRISTOPHER STENNING | 2023-10-18 15:26 | 2024-03-17 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-02-02 | 110705 |  | 7 | MXINTADM | GBOPP1 | Committed to WO #72302659
Z110094 | SCREEN, LAYERED MESH, 316L SS, 160 CM, TOP, O/D 1592.4 MM X | F3865-947 | 5 | ROCKY MOUNTAIN PROCESS ¦ | CHRISTOPHER STENNING | 2023-10-18 15:46 | 2024-03-17 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-05-17 | 110705 |  | 4 | MXINTADM | GBOPP1 | Order arrives 60 days late for WO #72302659
Z110094 | SCREEN, LAYERED MESH, 316L SS, 160 CM, TOP, O/D 1592.4 MM X | F3865-948 | 5 | ROCKY MOUNTAIN PROCESS ¦ | CHRISTOPHER STENNING | 2023-10-18 15:58 | 2024-03-17 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-08-30 | 110705 |  | 3 | MXINTADM | GBOPP1 | Order arrives 165 days late for WO #72302659
Z110097 | GASKET, 1/8" X 1/2" CS X 64.00" OD, FOR 160 CM, EPDM | F3865-1706 | 1 | EASTERN RIVERS INC ¦ | CHRISTOPHER STENNING | 2023-12-20 14:31 | 2024-02-09 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-02-09 | 1855-3C-1 | 1855-3C-1 | 4 | MXINTADM | EASTERN2 | Committed to WO #72302659
Z110122 | BALLAST, DIMMING, T5 SINGLE LAMP, 120V, 54W | C3865-2565 | 2 | GRANITE CITY ELECTRIC SUPPLY ¦ ------ REF QUOTE # S008643991 --- PLEASE EXPEDITE IF POSSIBLE | ALEXANDREA TONDREAU | 2022-06-28 11:40 | 2022-06-10 | APPR | FERGUSON INDUSTRIAL GROUP | 2022-09-30 | H3DT554CU110 |  | 1 | MXINTADM | LUTRON1 |  | No WOs requiring this part
Z111926 | DIAPHRAGM, SZ 2 INH, PLATINUM CURE SILICONE | F3865-1818 | 1 | EMD MILLIPORE CORP ¦ | CHRISTOPHER STENNING | 2024-01-05 14:06 | 2024-01-26 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-26 | NA51/26 | NA51/26 | 1 | MXINTADM | NOVASEP1 |  | No WOs requiring this part
Z120336 | GASKET, ENVELOPE, 1", USP CLASS VI, EPDM/PTFE, COMPOUND 6C.2 AND 6C.4, APPLICATION 6C.6 | M100145931 | 1 | INTERNAL TRANSFER PO - TOS01 TO RIS01 | CHRISTOPHER STENNING | 2022-09-30 17:20 | 2022-09-30 | APPR |  |  | 40RX-GR-E-1 |  | 5 | CHRISTOPHER STENNING | NEWMANS2 | Committed to WO #72070760
Z120358 | GASKET, SCREEN, 2", 10 MESH, USP CLASS VI, EPDM, COMPOUND 6C.4, APPLICATION 6C.6 | C3865-3238 | 1 | NEWMAN SANITARY GASKET COMPANY ¦ | CHRISTOPHER STENNING | 2022-07-05 12:40 | 2022-10-28 | APPR | FERGUSON INDUSTRIAL GROUP | 2022-10-28 | 40RXES0200 |  | 12 | MXINTADM | NEWMANS2 |  | No WOs requiring this part
Z120482 | O-RING, EPDM, 210, USP CLASS VI, COMPOUND 6C.4, APPLICATION | F3865-1790 | 1 | NEWMAN SANITARY GASKET CO ¦ -- QUOTE # 0057455 -- | CHRISTOPHER STENNING | 2024-01-04 14:32 | 2024-01-19 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-19 | Z120482 |  | 30 | MXINTADM | NEWMANS2 | Committed to WO #72320995
Z128464 | PROBE, PH, 120MM LG, INPRO 3253, TEFLON | E3865-2607 | 1 | FISHER SCIENTIFIC ¦ ----- REF QUOTE # 3104-7371-39 | ALEXANDREA TONDREAU | 2023-04-14 09:51 | 2023-04-28 | APPR | FERGUSON INDUSTRIAL GROUP | 2023-04-28 | 52002567 |  | 12 | MXINTADM |  |  | No WOs requiring this part
Z128555 | VALVE,RELIEF, 1", TRI-CLAMP INLET, 1-1/2", 150 PSI, 316L SS | F3865-1582 | 4 | FW WEBB CO ¦ | CHRISTOPHER STENNING | 2023-12-09 09:42 | 2024-01-18 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-18 | 4834.7704 |  | 1 | MXINTADM | LESER1 |  | No WOs requiring this part
Z128936 | O-RING, PLATINUM CURE SILICONE, CLASS VI, IND STD 346, COMPO | F3865-1228 | 1 | NEWMAN SANITARY GASKET CO ¦ QUOTE # 0056428 | CHRISTOPHER STENNING | 2023-11-07 14:05 | 2024-02-02 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-02-02 | USP-346-4749 |  | 8 | MXINTADM | NEWMANS1 |  | No WOs requiring this part
Z129125 | SENSOR, EC, RNG 1 TO 300 PPM, DRAGER SENSOR H2O2 HYDROGEN PE | F3865-1784 | 1 | DRAEGER INC ¦ REF QUOTE#: DRG-010424-MLZ-FER | BRYAN COLBURN | 2024-01-04 12:21 | 2024-02-09 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-02-09 | 6809705 |  | 1 | MXINTADM | DRAEGER1 | Committed to WO #71624825
Z129399 | O-RING, RED, VQM, IND STD 238, APPLICATION 6C.7, SILICONE | F3865-1796 | 1 | GARLOCK HYGIENIC TECHNOLOGIES ¦ QUOTE # Q57733 | CHRISTOPHER STENNING | 2024-01-04 15:33 | 2024-01-26 | APPR | FERGUSON INDUSTRIAL GROUP | 2024-01-26 | 238PEROXSIL-VI-RED |  | 58 | MXINTADM | RUBBERF1 | Committed to WO #72070760
SHOW ALL ROWS
SORT ASC.
SORT DESC.
RESERVED
PARTS
LATE DELIVERY
HELP
MAIN
Click on HELP again to hide this.
RIGHT CLICK on a cell will bring you either to the Reserved worksheet or the Parts worksheet, displaying only that part.
Have Maximo open and double click on a hyperlink will bring you to that record.
LATE DELIVERY will display only those rows where the Vendor Delivery date is later than the Required Date
SHOW ALL ROWS will display all records
SORT ASC./SORT DESC. will sort the list based on the selected columns. Note: This worksheet is protected, the password is "aaa", AutoFiltering works, howver you cannot sort a protected document using the sort feature in the AutoFilter.
MAIN, RESERVED, PARTS brings you to those worksheets.

## Parts
|  |  | Total Rows: | 35 | Lasted updated at 1/9/2024 2:03:56 PM |  |  | Filter: Inventory.Location = 'XXX01' | [19 empty] | Only 1% are repairable
|  |  | Visible Rows: | 35
i.Itemnum | Unit | t.Description | i.Catalogcode | i.ModelNum | i.Manufacturer | Vendor | i.Status | i.ABCType | iXBinNum | i.LastIssueDate | i.ccf | i.Category | RI_Balance | pl.OrderQty | r.ReservedQty | i.DeliveryTime | i.Issue1YrAgo | i.IssueYTD | i.MaxLevel | i.MinLevel | i.OrderQty | i.RMS | i.AvgCost | i.StandCost | i.AssignedTo | t.PCS | t.CommodityGroup | i.Repairable
Z # | Unit | Part Description | Catalog Code | Model Number | Manufacturer | Vendor | Status | ABC | Bin # | Last Issued | CCF | Category | RI Balance | Current Order Qty | Reserved | Delivery Time | Issue 1 Yr Ago | Issued YTD | Max | Min | Part Order Quantity | RMS Flag | Avg. Cost | Stand. Cost | Assigned To | PCS | Commodity Group | Repairable
LOCK OUT | EA | SWITCH, ELECTROSWITCH TYPE 86 / 86T LOCK OUT SWITCH |  | 7830K | SQUARE D |  | INACTIVE | C |  |  | 360 | NS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 600 | 600 | Peter Parker | 0 | MROELE | 0
XX00327 | EA | REDUCER |  | EURO-TRIX | PHOENIX |  | ACTIVE | N | NEW |  | 0 | NS |  | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 1 | 0 | 0.011 | 0.011 | Reed Richards | 0 | MAINT | 0
XX00585 | EA | VALVE,BALL, 1 PIECE, 1", SW, BRASS BODY | 70-205-01 | 70-205-0XX | APOLLO | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | N |  |  | 0 | NS | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 1133.68 | 1133.68 | Peter Parker | 0 | MROSUP | 0
XX00704 | EA | GAUGE,PRESSURE, 0-160 PSI RANGE, 2-1/2" DIAL, 1/4" NPT, 304 SS CASE, 316 SS TUBE, 316 SS, LOWER, NON FILLED | 25-1009SW-02L 160 | 25-XX009SW-02LXX60# | ASHCROFT | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | N |  | 2012-08-11 | 0 | NS |  | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 1 | 0 | 448.8 | 5555.1144 | Peter Parker | 1 | MROSUP | 0
XX01152 | EA | GASKET, 0.75", USP CLASS VI, TEFLON | 42RX-G-0.75 | 42MP-G-.75 | NEWMAN SANITARY GASKET | PERRIGO INC | OBSOLETE | N |  | 2008-03-06 | 0 | NS |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 1 | 0 | 0.722 | 0.722 | Susan Storm | 0 | ETVPS | 0
XX01155 | EA | GASKET, FDA SANITARY, SZ 1 INCH, TEFLON, CLASS VI | 40RX-G-1 | 40MP-G-XX | NEWMAN SANITARY GASKET | PERRIGO INC | OBSOLETE | N |  | 2008-04-21 | 0 | NS |  | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 1 | 0 | 0.78 | 0.78 | Susan Storm | 1 | ETVPS | 0
XX01156 | EA | GASKET, FDA SANITARY, SZ 1.5 INCH, TEFLON, CLASS VI, TRI-CLAMP | 40RX-G-1-1/2 | 40MPG-XX50 | NEWMAN SANITARY GASKET | PERRIGO INC | OBSOLETE | N |  | 2008-03-13 | 0 | NS |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 1 | 0 | 0.722 | 0.722 | Susan Storm | 1 | ETVPS | 0
XX01159 | EA | GASKET, FDA SANITARY, SZ 2 INCH, TEFLON, CLASS VI, TRI-CLAMP | 40RX-G-2 | 40MP-G-2 | NEWMAN SANITARY GASKET | PERRIGO INC | OBSOLETE | N | 21-JX3 | 2008-06-16 | 0 | NS |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 1 | 0 | 0.855 | 0.855 | Susan Storm | 1 | ETVPS | 0
XX01163 | EA | GASKET, SZ 2.5 INCH, TEFLON, CLASS VI, SANITARY | 40MPG-250 | 40MP-G-2-XX/2 | NEWMAN SANITARY GASKET | FW WEBB COMPANYDBA WEBB BIO PHARM | OBSOLETE | N |  | 2007-08-04 | 0 | NS |  | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 1 | 0 | 0.55 | 0.55 | Susan Storm | 0 | ETVPS | 0
XX01166 | EA | GASKET, SZ 3 INCH, TEFLON, CLASS VI, SANITARY | 40MP-G-3 | 40MP-G-3 | NEWMAN SANITARY GASKET | PERRIGO INC | OBSOLETE | N |  | 2009-01-04 | 0 | NS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 22.655 | 22.655 | Susan Storm | 1 | ETVPS | 0
XX01168 | EA | GASKET, ENVELOPE, SZ 3 INCH, TEFLON/EPDM, CLASS VI | 40MP-GR-3" | 0-A40MP-GR3 | NEWMAN SANITARY GASKET | PERRIGO INC | OBSOLETE | N |  | 2008-02-13 | 0 | NS |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 1 | 0 | 22.055 | 22.055 | Susan Storm | 1 | ETVPS | 0
XX01174 | EA | CLAMP, 1-1/2", SS, SANITARY, 3 PIECE | 13MHHS-1.5-S | XX3MHHS-XX.5-S | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | CENTRAL STATES INDUSTRIAL EQUIPMENTSVC INC | ACTIVE | C | 22-CX7 | 2023-10-12 | 360 | STK | 9 | 0 | 0 | 31 | 3 | 0 | 12 | 4 | 1 | 0 | 7.722 | 110.116 | Reed Richards | 0 | MAINT | 0
XX01188 | EA | ELBOW, 1/2", TRI-CLAMP, 316L SS, 240/EP, 90 DEG | B2CMP-.5-316L-PM | B2CMP-.5-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | PERRIGO INC | ACTIVE | N | 10-KX3 | 2015-09-22 | 0 | NS | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 1 | 0 | 5544.448 | 0 | Reed Richards | 1 | MAINT | 0
XX01194 | EA | ELBOW:3/4",TRI-CLAMP,316L SS,240/EP,90 DEG, SHORT RADIUS | B2CMP-.75-316L-PM | B2CMP-.75-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | C | 21-AX2 | 2022-04-05 | 360 | STK | 15 | 0 | 0 | 17 | 0 | 0 | 20 | 10 | 1 | 0 | 336.5522 | 557.844 | Reed Richards | 1 | MAINT | 0
XX01203 | EA | ELBOW, 1", TRI-CLAMP, 316L SS, 240/EP, 90 DEG | B2CMP-1-316L-PM | B2CMP-XX-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | C | 36-IX3 | 2012-05-01 | 0 | STK | 10 | 0 | 0 | 30 | 0 | 0 | 10 | 5 | 1 | 0 | 446.2255 | 446.08 | Reed Richards | 1 | MAINT | 0
XX01208 | EA | ELBOW, 1-1/2", TRI-CLAMP, SS, 45 DEG | 2KMP-1.5 | 2KMP-XX.5 | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | N | 36-CX6 | 2021-01-01 | 0 | NS | 12 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 449.449 | 4411.55 | Reed Richards | 0 | MAINT | 0
XX01210 | EA | ELBOW, 1-1/2", TRI-CLAMP, 316L SS, 240/EP, 90 DEG | B2CMP-1.5-316L-PM | B2CMP-XX.5-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | C | 15-IX5 | 2023-10-05 | 360 | STK | 8 | 1 | 0 | 17 | 12 | 0 | 10 | 5 | 1 | 0 | 4411.2211 | 550.755 | Reed Richards | 1 | MAINT | 0
XX01212 | EA | ELBOW, 2", TRI-CLAMP, SS, 45 DEG |  | B2KMP-2-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FERGUSON INDUSTRIAL GROUP | ACTIVE | C | 19-EX1 | 2022-11-23 | 0 | STK | 1 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 1 | 0 | 622.229 | 0 | Reed Richards | 0 | MAINT | 0
XX01215 | EA | ELBOW, 2", TRI-CLAMP, 316L SS, 240/EP, 90 DEG | B2CMP-2-316L-PM | B2CMP-2-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | PERRIGO INC | ACTIVE | C | 15-IX5 | 2020-05-05 | 0 | STK | 18 | 0 | 0 | 44 | 0 | 0 | 10 | 5 | 1 | 0 | 447.3333 | 446.55 | Reed Richards | 0 | MAINT | 0
XX01228 | EA | CAP, PORT, 2", 316L SS, 240/EP | A16C-2 | XX6AMP2-3XX6L-PM | ALFA LAVAL INC | CENTRAL STATES INDUSTRIAL EQUIPMENTSVC INC | ACTIVE | C | 11-EX2 | 2023-05-03 | 360 | STK | 20 | 0 | 0 | 19 | 11 | 0 | 20 | 10 | 1 | 0 | 9.78 | 110.446 | Reed Richards | 1 | MAINT | 0
XX01229 | EA | CAP, PORT, 3", 316L SS, 240/EP | A61C-3 | XX6AMP3-3XX6L-PM | ALFA LAVAL INC | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | C | 12-GX3 | 2023-12-01 | 0 | STK | 6 | 3 | 0 | 45 | 9 | 0 | 10 | 5 | 1 | 0 | 2255.559 | 330.822 | Reed Richards | 1 | MAINT | 0
XX01230 | EA | CAP, PORT, 4", 316L SS, 240/EP |  | XX6AMP-4-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | C | 11-EX2 | 2023-02-02 | 360 | STK | 4 | 4 | 0 | 12 | 5 | 0 | 8 | 4 | 1 | 0 | 550.755 | 69.79 | Reed Richards | 1 | MAINT | 0
XX01233 | EA | CAP, END, SZ 0.5 & 0.75 INCH, 316L SS, 240EP | TEG16AL-5/75-PM | XX6AMP-.75-3XX6L-PM | ALFA LAVAL INC | CENTRAL STATES INDUSTRIAL EQUIPMENTSVC INC | ACTIVE | A | 38-IX3 | 2023-09-14 | 90 | STK | 165 | 10 | 0 | 18 | 414 | 0 | 200 | 100 | 1 | 0 | 1122.2255 | 110.1133 | Reed Richards | 1 | MROSUP | 0
XX01234 | EA | CAP, PORT, 6", 316L SS, 240/EP | 16AMP-6-316L-PM | XX6AMP-6-3XX6L-PM | ITT SHEROTEC | PERRIGO INC | ACTIVE | N | 20-HX2 | 2023-10-09 | 0 | NS | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 0 | 1 | 0 | 33228.655 | 0 | Peter Parker | 1 | MAINT | 0
XX01261 | EA | FERRULE, TC-AW LONG, 3", SS, 240EP |  | BSXX4AM-3-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | PERRIGO INC | ACTIVE | N |  | 2009-01-26 | 0 | NS |  | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 1 | 0 | 3311.44 | 3311.44 | Reed Richards | 1 | MAINT | 0
XX01296 | EA | TEE, 3/4", TRI-CLAMP, SS | B7MP-.75-316L-PM | B7MP-.75-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | N | 25-BX4 | 2010-10-01 | 0 | NS | 2 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 1 | 0 | 86.446 | 86.446 | Reed Richards | 0 | MAINT | 0
XX01310 | EA | TEE, 1", TRI-CLAMP, SS | B7MP-1"-316L-PM | B7MP-XX-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | N | 25-DX6 | 2020-07-17 | 0 | NS | 6 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 1 | 0 | 77.2222 | 77.2222 | Reed Richards | 0 | MAINT | 0
XX01318 | EA | TEE, REDUCING, 1" X 1" X 1/2", TRI-CLAMP, 316L SS, 15RA | B7RMPS-1X.5-316L-PM | TCLB7RMPSXXXXX23XX6LPL | ABEC INC | ABEC INC | INACTIVE | N |  | 2017-09-26 | 0 | NS |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 1 | 0 | 11556.2255 | 1177.3344 | SHEILA CORSE | 0 | MAINT | 0
XX01358 | EA | TEE, 2", TRI-CLAMP, SS | A7CCC2"TC | B7MP-2-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | N | 22-DX5 | 2020-06-09 | 0 | NS | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 611.55 | 611.55 | Reed Richards | 1 | MAINT | 0
XX01402 | EA | REDUCER, CONCENTRIC, SZ 2 X 1 INCH, 316L SS | B31-2X1-316L-PM | B3XXXX4MP-2XXX-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | N | 13-HX5 | 2011-04-05 | 0 | NS | 4 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 11118.55 | 11118.55 | Reed Richards | 1 | MAINT | 0
XX01412 | EA | REDUCER,PIPE, ECCENTRIC, 1" X 1/2", TC X TC, 316L SS, FINISH ID 15RA, FINISH OD ANNEALED | B32-14MP-1X.5-316L-PM | B32-XX4MP-XXX.5-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | PERRIGO INC | ACTIVE | N |  |  | 0 | NS |  | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Reed Richards | 0 | MAINT | 0
XX01418 | EA | REDUCER,PIPE, CONCENTRIC, 2" X 1-1/2", TC X TC, SS | OLD# B31-14MP-2X1.5-316L-PM | B3XX-XX4MP-2XXX.5-3XX6L-PM | ALPHA LAVAL | PERRIGO INC | ACTIVE | C | 13-GX6 | 2020-01-16 | 0 | STK | 6 | 0 | 0 | 34 | 0 | 0 | 1 | 0 | 1 | 0 | 559.1111 | 90.5555 | Reed Richards | 1 | MAINT | 0
XX01420 | EA | REDUCER,PIPE, CONCENTRIC, 1-1/2" X 1", TRI-CLAMP, 316L SS, 240/EP | B31-14MP-1.5X1-316L-PM | B3XX-XX4MP-XX.5XXX-3XX6L-PM | TRI-CLOVER, SUBSIDIARY OF ALFA LAVAL | FW WEBB COMPANYDBA WEBB BIO PHARM | ACTIVE | C | 36-FX2 | 2021-11-22 | 360 | STK | 52 | 0 | 0 | 7 | 0 | 0 | 10 | 5 | 1 | 0 | 911.68 | 96.6 | Reed Richards | 0 | MAINT | 0
XX01421 | EA | REDUCER, PIPE, CONCENTRIC, 1-1/2" X 3/4", TRI-CLAMP, 316L SS, 240/EP, 3" OAL | TEG31CC6L1.5X.75-PD | B3XXXX4MP-XXXX/2X3/4-3XX6L-PM | ALFA LAVAL INC | PERRIGO INC | ACTIVE | C | 15-JX3 | 2020-07-01 | 360 | STK | 10 | 0 | 0 | 32 | 0 | 0 | 10 | 5 | 1 | 0 | 11755.955 | 114433.11 | Reed Richards | 1 | MAINT | 0
XX01471 | EA | ELBOW,TUBE ADAPTER, 1/4", MNPT, TUBE | KQL07-35S | KQL07-35S | SMC CORPORATION OF AMERICA | MOTION INDUSTRIES INC | ACTIVE | N |  |  | 0 | NS |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 22.011 | 22.011 | Reed Richards | 0 | MAINT | 0
SHOW ALL ROWS
SORT ASC.
RESERVED
HELP
MAIN
ORDERS
SORT DESC.
Click on HELP again to hide this.
RIGHT CLICK on a cell will bring you to a list of orders for that part, or jump to the reserve screen displaying only that part.
Have Maximo open and double click on a hyperlink will bring you to that record.
SHOW ALL ROWS will display all records
SHOW ALL COLUMNS/HIDE SOME COLUMNS will toggle additional columns
SORT ASC./SORT DESC. will sort the list based on the selected columns. Note: This worksheet is protected, the password is "aaa", AutoFiltering works, howver you cannot sort a protected document using the sort feature in the AutoFilter.
MAIN, RESERVED, ORDERS brings you to those worksheets.
SHOW STOCKOUTS